## Slide 1
WADHWANI ELECTRONICS LAB · EE 214
Mini-DAQ — Progress Update
What’s changed since the last review — the HLS FFT is built, verified, and packaged; the build has crossed from algorithm work into system integration.
Jaivardhan Jain
FPGA Research Intern — Wadhwani Electronics Lab, IIT Bombay · Progress update, Day 9

## Slide 2
SINCE THE LAST REVIEW
From “FFT to synthesize” to “FFT done”
HLS FFT: synthesized → shipped
Last review it was still to be synthesized and accuracy-checked. Now built, verified 4/4, and packaged as an AXI-Stream IP.
Biggest unknown — resolved
Fixed-point FFT accuracy was the flagged risk. Measured error ~1e-4; Q5.15 format chosen (Q1.15 would overflow). Risk retired.
Optimized, not just working
Float baseline 90 DSP (100% of the chip) → Q5.15 12 DSP (13%). Stream interval cut 113 → 20 cycles.
Integration path locked
Committed to a MicroBlaze SoC; the XADC + UART blocks reuse existing hand-written VHDL controllers.
THE SHIFT
The project has crossed from algorithm work into system integration. The hardest technical piece — the FFT — is done and verified. What remains is wiring, embedded software, and board bring-up.
Phase 1: ~55% · Project: ~45%
Since the last review
2

## Slide 3
HLS FFT · COMPLETED
The FFT is done — verified and optimized
The one active engineering block from the last review is finished: built as a dataflow kernel, verified against the golden model, tuned to fixed-point, and packaged as an IP.
Verified end-to-end
csim + cosim both 4/4 vs the Python golden vectors — the generated RTL matches the C, cycle-accurate.
Fixed-point nailed down
Q5.15 (ap_fixed<20,5>): the 5 integer bits hold FFT bit-growth; Q1.15 would overflow at the DC bin. Peak error ~1e-4.
Area + throughput win
Float→fixed cut DSP 90→12 (13% of the chip); a dataflow region cut the stream interval 113→20 cycles.
RESULT — FFT COMPLETE
12 DSP / 1629 LUT / 1937 FF — 13% of the XC7A35T
151.77 MHz (target 100 MHz)
Latency 113 / interval 20 cycles
Packaged AXI-Stream IP (fft_axis 1.0)
Status: verified, synthesized, exported — done
HLS FFT — completed
3

## Slide 4
HLS FFT · INTERFACE & THROUGHPUT
From array ports to a free-running stream
Beyond “it synthesizes”: the verified core was re-interfaced for the DAQ pipeline and tuned so frames flow continuously.
113 → 20
cycle interval
5.6× throughput — made fft_axis a dataflow region so read / compute / write overlap.
40-bit
AXI-Stream TDATA
one complex Q5.15 sample per beat; TLAST marks each 16-point frame.
ap_ctrl_none
free-running control
data-driven, no start/done handshake — ideal for a continuous XADC feed.
Same verified core, re-wrapped: streamed, made free-running, and exported to the Vivado IP catalog — still cosim-clean 4/4.
HLS FFT — interface & throughput
4

## Slide 5
MINI-DAQ · PLAN CHANGES
What changed in the plan
SCOPE CHANGES
Hand-RTL FFT → optional stretch — other RTL projects already cover that ground; not required for the portfolio.
The HLS FFT IP is now THE system FFT — no dual-track dependency.
Number format corrected Q1.15 → Q5.15 for bit-growth headroom.
DECISIONS LOCKED
Integration via a MicroBlaze SoC — chosen to enable Phase-4 SPI-flash standalone boot.
XADC + UART: reuse the existing hand-written VHDL controllers (verify, don’t rebuild).
The free-running FFT streams to MicroBlaze over AXI (DMA or AXI-Stream FIFO).
Plan changes & decisions
5

## Slide 6
MINI-DAQ · CURRENT STATUS
Where Phase 1 stands
~55%
of Phase 1 complete
~45%
of the entire project
DONE
Golden model + test vectors
HLS FFT — verified (csim+cosim 4/4), Q5.15, AXI-Stream, IP exported
BUILT — TO VERIFY
XADC controller (VHDL)
UART controller (VHDL)
NEXT
MicroBlaze integration + glue (AXI wrappers, XADC→AXIS, DMA/FIFO)
Embedded C — frame & stream results over UART
Python visualization
Hardware end-to-end bring-up
Current status
6

## Slide 7
MINI-DAQ · NEXT
Day 9 — system integration bring-up
THE PLAN
Verify the existing XADC & UART VHDL controllers in simulation.
Stand up the MicroBlaze block design with the FFT IP.
Build the glue: AXI wrappers for the controllers, XADC→AXIS adapter, DMA/FIFO path.
Wire XADC → FFT → MicroBlaze → UART; software formats and streams each frame.
BIGGEST UNKNOWN — UPDATED
The FFT-accuracy risk is retired. The new unknown is integration: attaching the custom VHDL controllers to the AXI fabric, and the first on-board bring-up — clocking, handshakes, and byte framing.
Blocker: the XADC / UART VHDL sources still need adding to rtl/.
Next steps
7

## Slide 8
SUMMARY
Updated roadmap
Done
HLS FFT — verified 4/4, Q5.15, AXI-Stream, IP exported
Golden model + test vectors
JTAG verification pipeline (prior work)
In Progress
MicroBlaze SoC integration
Verify XADC + UART VHDL controllers
Phase 1 wiring (~55%)
Next
End-to-end demo: XADC→FFT→UART→Python
Phase 4: SPI-flash standalone boot
Optional: hand-RTL FFT + RTL-vs-HLS
Roadmap
8